## W1
PROJECT REPORT
Group | E - Learning Team
Week | 13/01/2025 - 19/01/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
| Complete project plan, create SRS | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
| Review and Update SRS | All team | 21/01/2025
| Database design + Review database design | All team | 08/02/2025 | Decide database type: SQL Sever Management
| Analysis and selection of Frontend technology | Pham Thanh Vu | 09/02/2025
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes