## W1
PROJECT REPORT
Group | E - Learning Team
Week | 13/01/2025 - 19/01/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
| Complete project plan, create SRS | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
| Review and Update SRS | All team | 21/01/2025
| Database design + Review database design | All team | 08/02/2025 | Decide database type: SQL Sever Management
| Design and build database | Nguyen Duc Hoang Nam | 09/02/2025 | Completed the initial design of the database schema, including tables, relationships, and constraints. Defined key entities and attributes required for the project. Set up the development environment for database creation (e.g., MySQL/PostgreSQL/SQL Server). Created scripts to implement the schema design. Tested basic CRUD operations to ensure tables and relationships are functioning as expected.
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
| Recommend using Asana or Trello to track work progress, making it more transparent and easier to manage. | Le Khanh Duc | 2025-02-10 | Makes progress transparent and easier to track
| Swagger integration for documentation automation | Le Khanh Duc | 2025-02-10 | Support API documentation management and testing