## W1
PROJECT REPORT
Group | E - Learning Team
Week | 13/01/2025 - 19/01/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
| Complete project plan, create SRS | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
| Review and Update SRS | All team | 21/01/2025
| Database design + Review database design | All team | 08/02/2025 | Decide database type: SQL Sever Management
| Analysis and selection of Backend technology | Le Khanh Duc | 09/02/2025 | Analyze the suitability of ASP.NET Core Web API for backend development based on its scalability, integration with SQL Server, and support for RESTful services. Focus on leveraging Entity Framework Core for database interaction and ensuring team alignment on architecture.
| Implement authentication & authorization for backend security. | Le Khanh Duc | 09/02/2025 | Implement authentication & authorization in ASP.NET Core. Focus on security best practices, token-based authentication (JWT), and role-based access control (RBAC) to ensure secure API access
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
| Recommend using Asana or Trello to track work progress, making it more transparent and easier to manage. | Le Khanh Duc | 2025-02-10 | Makes progress transparent and easier to track
| Swagger integration for documentation automation | Le Khanh Duc | 2025-02-10 | Support API documentation management and testing
| Home page, login, register, profile design | Le Khanh Duc | 2025-03-02 | Design frontend application
| Create Course, Forgotpassword, ChangePassword, Update Profile | Le Khanh Duc | 2025-03-08 | Code backend and intergration frontend
| Create Post, Create Ads | Le Khanh Duc | 2025-03-18 | Code backend and intergration frontend (Post, Ads, Contact)