## Team 2
Date | Duration (h) | Timeframe | Topic | Status
2025-01-11 | 8 | 08:00-17:30 | Mock Project - Day 1 - Kick off + Create requirement outline | Done
2025-01-12 | 8 | 08:00-17:30 | Mock Project - Day 2 - Create SRS | Started
2025-01-21 | 8 | 08:00-17:30 | Mock Project - Day 3 - Review and update SRS
2025-01-23 | 8 | 08:00-17:30 | Mock Project - Day 4 - Database Design + Review Database Design
2025-02-06 | 8 | 08:00-17:30 | Mock Project - Day 5 - Create Blackbox Testcase
2025-02-15 | 8 | 08:00-17:30 | Mock Project - Day 6 - Review and update Blackbox TC
2025-02-18 | 8 | 08:00-17:30 | Mock Project - Day 7 - Coding
2025-02-20 | 8 | 08:00-17:30 | Mock Project - Day 8 - Coding
2025-02-25 | 8 | 08:00-17:30 | Mock Project - Day 9 - Coding
2025-02-27 | 8 | 08:00-17:30 | Mock Project - Day 10 - Coding
2025-03-04 | 8 | 08:00-17:30 | Mock Project - Day 11 - Review code + UT
2025-03-06 | 8 | 08:00-17:30 | Mock Project - Day 12 - UT
2025-03-11 | 8 | 08:00-17:30 | Mock Project - Day 13 - IT
2025-03-13 | 8 | 08:00-17:30 | Mock Project - Day 14 - IT + Create Test Report
2025-03-18 | 8 | 08:00-17:30 | Mock Project - Day 15 - Final Report
2025-03-20 | 8 | 08:00-17:30 | Mock Project - Day 16 - Final Report (cont)
2025-03-25 | 8 | 08:00-17:30 | Sum-up and Closing Ceremony
Tên đề tài: | Xây dựng website quản lý và mua bán khóa học online
Lê Khánh Đức
Phạm Thanh Vũ
Nguyễn Đức Hoàng Nam