## W1
PROJECT REPORT
Group | FLearning Team
Week | 14/12/2022 - 21/12/2022
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
| Hoàn thành Project plan nộp BM và P. TCQLĐT | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
| Define Database Schema | Quang + Minh | 13/01/2023 | Decide database type: SQL or NoSQL
| Define layout & script for JPD123 course | Phúc + Nhi | 13/01/2023
| Define overall project | Quang + Khôi | 13/01/2023 | Project workflow, project source code control, project document source...
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes